## Formal Instr
Task 1 - MODEL ANSWER CONTENT
For each of the three component documents listed below, describe in your own words it’s: a) appearance and contents, and b) purpose &/or role in the contract
Appearance and content |  | Purpose |  | Role in contract
1. Formal Instrument
2-4 page document (usually at front of contract documents) | 0.5 | To formalise the agreement (offer & acceptance) which 'formed the contract' in a comprehensive, stand-alone, summary document. | 1 | Provides one document that evidences the contract rather than multiple documents that culminated in the final egreement | 0.5
Agreement document: | 0.5 |  |  | Provides the Contract date if there has been no previous 'acceptance' (ie. contract is formed when FIA is executed | 0.5
# Between two parties (named) | 0.5 | To clarify the contract by distilling all previous documentation and correspondence into a single document that encapsulates the entire agreement. | 0.5 | Clearly defines which documents form part of the contract, and which do not | 0.5
# Dated & signed by both parties | 0.5 |  |  | Specifies precedence of documents | 0.5
# Witnessed | 0.5 | To clearly define which documents form part of the contract, and which do not - thereby eliminating future disputes and optimising administration efficiency. | 0.5 | Nominates contract sum or nominates the contract pricing document | 0.5
# Sometimes requires company seal | 0.5
# Sometimes in form of deed | 0.5
Usually more than one topic of agreement listed on document (ie. multiple agreements) | 0.5
Other correct answer | 0.5 | Other correct answer | 0.5 | Other correct answer | 0.5
Max: | 2 | Max: | 1.5 | Max: | 1.5
|  |  |  | Maximum Possible Marks: | 5

## AS4000 GC's
Task 1 - MODEL ANSWER CONTENT
For each of the three component documents listed below, describe in your own words it’s: a) appearance and contents, and b) purpose &/or role in the contract
Appearance and content |  | Purpose |  | Role in contract
2. AS4000-1997 - General conditions of contract
A4 document approx 70 pages (including Annexure) | 0.5 | To specify rights and obligations of both parties | 0.5 | Informs the parties and Superintendent of their rights, obligations and risks | 0.5
Published & distributed by SAI Global | 0.5 | To allocate risk between parties | 0.5 | Provides procedures and rules for administration | 0.5
Copyright owned by Standards Australia | 0.5 | To specify terms and conditions under which the contract is to operate (ie. rules to govern the contract process) | 0.5 | Provides a first point of refence for resolving discrepancies or dispiutes | 0.5
Standard (general) conditions of contract for construction contracts in Australia | 0.5 | To provide rules of 'conduct' of the parties in various circumstances | 0.5 | Other correct role. | 0.5
'Contents' page organised by clause number | 0.5 | To specify the role of the Superintendent | 0.5
Cl 1 contains a comprehensive list of 'definitions' for terms used | 0.5
Body of document oganised by clause number and title with sub-clause numbers and titles where required | 0.5 | Note: Annexure provides standard variables (Part A) to inform the body of document and also any non-standard variables (Part B). Not required for this task. | 0.5
Extensive 'Index' for locating relevent clauses | 0.5
Other correct answer | 0.5 | Other correct answer | 0.5 | Other correct answer | 0.5
Max: | 1.5 | Max: | 2 | Max: | 1.5
|  |  |  | Maximum Possible Marks: | 5

## Part A
Task 1 - MODEL ANSWER CONTENT
For each of the three component documents listed below, describe in your own words it’s: a) appearance and contents, and b) purpose &/or role in the contract
Appearance and content |  | Purpose |  | Role in contract
3. Annexure Part A
First part of an attachment to the general conditions | 0.5 | Provides details of project specific (standard) variables referenced in body of the general conditions | 1.5 | Used to identify variables referenced in body of the general conditions | 1.5
9 pages of details to be completed by the parties | 0.5 |  |  | Part A - Separable Portions specifies those variables that change for each SP. | 1
Last 2 pages are relevant to separable portions | 0.5
Each variable is identified with an Item number and includes a reference to the relevant clause in the general conditions | 0.5
Some items provide a 'default' value | 0.5
Other correct answer | 0.5 | Other correct answer | 0.5 | Other correct answer | 0.5
Max: | 2 | Max: | 1.5 | Max: | 1.5
|  |  |  | Maximum Possible Marks: | 5

## Part B
Task 1 - MODEL ANSWER CONTENT
For each of the three component documents listed below, describe in your own words it’s: a) appearance and contents, and b) purpose &/or role in the contract
Appearance and content |  | Purpose |  | Role in contract
4. Annexure Part B
Second part of attachment to the general conditions | 1 | To provide non-standard variables/variations to the body of the document | 1 | Must be checked in every instance when the standard conditions are to be relied upon. | 1
Single page | 1 | Provides simple, traceable means of describing any adjustments made to standard conditions | 1 | For checking if any changes havbe been made to the body of the standard document | 1
Provides space for parties to list deletions, amendments and additions to standard conditions contained in body of AS4000 | 1 | “Special Conditions” can be listed here | 1
Other correct answer | 0.5 | Other correct answer | 0.5 | Other correct answer | 0.5
Max: | 2 | Max: | 2 | Max: | 1
|  |  |  | Maximum Possible Marks: | 5

## Scope
Task 1 - MODEL ANSWER CONTENT
For each of the three component documents listed below, describe in your own words it’s: a) appearance and contents, and b) purpose &/or role in the contract
Appearance and content |  | Purpose |  | Role in contract
5. Scope of Works
Short written document (typ. 2-10 pages) describing the work under the contract (WUC) | 1 | To describe the scope and extent of Contractor's work activities and responsibilities | 0.5 | To assist in determining:
Can be stand-alone document or included in a specification as a separate section | 0.5 | Delineate the physical extent of work included in contract | 0.5 | 1. whether something is part of WUC | 0.5
|  | To define work 'by others' | 0.5 | 2. which party is responsible for particular activities/actions | 0.5
|  | Often to describe management systems to be used by Contractor eg. QA reuirements | 0.5 | 3. which party is liable for certain risks | 0.5
|  | To emphasise things included that are necessary to complete the work but not shown/defined elsewhere | 0.5 | 4. whether a change constitues a variation | 0.5
|  |  |  | To specify responsibilities of the Contractor that do not form part of 'the Works' eg. Provision of site facilities for the Superintendent | 0.5
|  |  |  | To specify design and detailing responsibilities | 0.5
|  |  |  | To specify certifcation responsibilities | 0.5
Other correct answer | 0.5 | Other correct answer | 0.5 | Other correct answer | 0.5
Max: | 1 | Max: | 2 | Max: | 2
|  |  |  | Maximum Possible Marks: | 5

## Program
Task 1 - MODEL ANSWER CONTENT
For each of the three component documents listed below, describe in your own words it’s: a) appearance and contents, and b) purpose &/or role in the contract
Appearance and content |  | Purpose |  | Role in contract
6. Tender Program
Usually a barchart/gantt chart prepared at the time of tender | 0.5 | To summarise the activities reqired to complete 'the Works' (ie. WUC) | 1 | Used as basis for assessing the acceptability of a construction program provided by Contractor at Superintendent's request (Cl 32) | 2
Often highlights critical path | 0.5 | To describe the sequence and timing of activities on which the Contract is based. | 1 | If no construction program requested under Cl 32 then to act as the construction program for the purposes of the contract conditions. | 1
Sometimes consists of a simple list of activities/milestones and dates only | 0.5 | Highlight activities identified at tender time which are critical to achieve practical completion on the date for practical completion | 1
Can be any size (A4 to A0) and single or multiple pages | 0.5
Other correct answer | 0.5 | Other correct answer | 1 | Other correct answer | 1
Max: | 1.5 | Max: | 2 | Max: | 1.5
|  |  |  | Maximum Possible Marks: | 5

## BoQ
Task 1 - MODEL ANSWER CONTENT
For each of the three component documents listed below, describe in your own words it’s: a) appearance and contents, and b) purpose &/or role in the contract
Appearance and content |  | Purpose |  | Role in contract
7. Bill of Quantities
Usually stand-alone document (Typ. A4 size) |  | Provide details of how the contractor calculated the contract sum - Cl 1: 'contract sum' Item b) | 0.5 | May form part of the contract (hence supplement or replace the scope of work) – Cl: 2.2 Alt: 1 + Item: 10 a) | 0.5
Each page is a table with 6 columns labelled: Item No., Description, Unit, Qty, Rate and Amount | 0.5 | For measuring progress and valuing progress claims (Cl 37.1) | 0.5 | May not form part of the contract – Cl: 2.2 Alt: 2 + Item: 10 b). Provided for reference only. | 0.5
Often contains a summary bill followed by a bill detailing each item (trade) on the summary bill. | 0.5 | For valuing variations - Cl 36.4 c) | 0.5 | Schedules of unit rates may be included for work directed by the Superintendent - Cl 36.4 c) | 0.5
May show ‘Prelims’ in a separate bill or spread across work items in other bills | 0.5 | To quantify the contract sum if Alternative 1 applies - Cl 2.2 and Item 10(a) | 0.5 | - Alternative 1 must be priced as per Cl 2.3 - Alternative 2 is not priced unless required in Item 10 b) | 0.5
First 4 columns are always completed. Last 2 columns may or may not be (ie. bill is priced or not priced) . | 0.5 |  |  | For measuring progress and valuing progress claims (Cl 37.1) - For valuing variations - Cl 36.4 c) | 0.5
If last 2 columns completed (priced), each bill shows a total amount - total of summary bill is equal to the contract sum | 0.5
Lists any provisional items | 0.5
Other correct answer | 0.5 | Other correct answer | 0.5 | Other correct answer | 0.5
Max: | 2 | Max: | 1.5 | Max: | 1.5
|  |  |  | Maximum Possible Marks: | 5

## Spec
Task 1 - MODEL ANSWER CONTENT
For each of the three component documents listed below, describe in your own words it’s: a) appearance and contents, and b) purpose &/or role in the contract
Appearance and content |  | Purpose |  | Role in contract
8. Technical Specifications
Single or multiple written documents based on disciplines eg. Architectural, structural, services etc. | 0.5 | To 'specify' technical requirements for construction of the work defined on the drawings. eg. standards, materials, finishes, quality, design intent, etc. | 0.5 | Always used together with drawings to determine the design requirements for constructing the Works | 1
Organised in sections reflecting different ‘trades’ and/or ‘finishes’ | 0.5 | Sometimes to specify construction 'methods' to be adopted | 0.5 | To assist in determining: | 0.5
May include Scope of works (if not included elsewhere as a separate document) | 0.5 | To supplement construction drawings to provide full details for construction of the Works | 0.5 | - whether an item is part of WUC | 0.5
Responsible consultant clearly identified | 0.5 | To detail hold points/approvals required | 0.5 | - whether work has been completed satisfactorily | 0.5
Usually 'controlled' document with author, checker and revision noted | 0.5 | Usually to spacify the management systems and reporting required | 0.5 | - which party is responsible for action | 0.5
|  | Sometimes to nominate 'brand' of materials/equipment, often followed by "or approved equivalent" | 0.5 | - whether an item is a variation | 0.5
|  |  |  | For checking of completed work | 0.5
Other correct answer | 0.5 | Other correct answer | 0.5 | Other correct answer | 0.5
Max: | 1.5 | Max: | 2 | Max: | 1.5
|  |  |  | Maximum Possible Marks: | 5

## Drg's
Task 1 - MODEL ANSWER CONTENT
For each of the three component documents listed below, describe in your own words it’s: a) appearance and contents, and b) purpose &/or role in the contract
Appearance and content |  | Purpose |  | Role in contract
9. Construction Drawings
2-D representations (diagrams/drawings) of parts of the WUC drawn to scale | 0.5 | To provide a precise graphical representation of the work to be constructed | 0.5 | Always used together with specifications to determine the design requirements for constructing the Works | 1.5
Normally CAD drawings | 0.5 | To provide: |  | To assist in determining:
Original' sizes usually between A3 and A0. Often reduced to A3. | 0.5 | - Details for all aspects of construction | 0.5 | - whether an item is part of WUC | 0.5
Typ drawing includes: |  | - Engineering information | 0.5 | - whether work has been completed satisfactorily | 0.5
- Border with title block (incl project name, drg title, No. & Rev, scale, etc) | 0.5 | - Set out information | 0.5 | - which party is responsible for action | 0.5
- Line drawings of various views | 0.5 | - Dimensions | 0.5 | - whether an item is a variation | 0.5
- Dimensions and sometimes RL's | 0.5 |  |  | For checking of completed work | 0.5
- Sometimes schedules, notes, specifications, etc on body of drawing | 0.5
Other correct answer | 0.5 | Other correct answer | 0.5 | Other correct answer | 0.5
Max: | 2 | Max: | 1.5 | Max: | 1.5
|  |  |  | Maximum Possible Marks: | 5